## RICE Calculator
[Your Company] — Backlog Prioritization Calculator
RICE Framework ¦ Formula: RICE Score = (Reach × Impact × Confidence) ÷ Effort
Impact: 3=Massive ¦ 2=High ¦ 1=Medium ¦ 0.5=Low ¦ 0.25=Minimal Confidence: 100%=High ¦ 80%=Medium ¦ 50%=Low Effort: person-months
Backlog Item / User Story | Category | Reach (users/period) | Impact (0.25–3) | Confidence (0.5–1.0) | Effort (person-months) | RICE Score | Priority Rank | MoSCoW | Notes / Rationale
User Authentication — Login & Registration | Core Platform | 5000 | 3 | 100% | 1 |  |  | Must Have | Critical for product launch — no auth = no product
Password Reset via Email | Core Platform | 4500 | 2 | 100% | 0.5 |  |  | Must Have | High frequency support request — reduces costs
Dashboard — KPI Summary View | Analytics | 3000 | 2 | 80% | 1.5 |  |  | Must Have | First thing execs see — must be valuable and fast
Real-time Notifications (email + in-app) | Engagement | 2500 | 1 | 80% | 1 |  |  | Should Have | Improves engagement but not launch-critical
CSV Export for Reports | Reporting | 1800 | 1 | 100% | 0.5 |  |  | Should Have | Quick win — high confidence, low effort
Dark Mode UI Theme | UX Enhancement | 1200 | 0.5 | 50% | 1.5 |  |  | Could Have | Nice-to-have; low confidence of adoption
Advanced Search with Filters | Discovery | 2000 | 2 | 80% | 2 |  |  | Should Have | Important for power users; complex to build
Two-Factor Authentication (2FA) | Security | 3500 | 3 | 80% | 1.5 |  |  | Must Have | Compliance requirement — post-launch deadline
Mobile App — iOS Native | Mobile | 4000 | 3 | 50% | 8 |  |  | Could Have | Major platform extension — high effort, uncertain
AI-Powered Recommendations | Innovation | 1500 | 3 | 50% | 6 |  |  | Could Have | Differentiator but unproven — needs spike first
Bulk User Import (CSV Upload) | Admin | 1000 | 1 | 80% | 1 |  |  | Should Have | Admin time-saver; moderate priority
Audit Log & Activity History | Compliance | 2200 | 2 | 100% | 1.5 |  |  | Must Have | Regulatory requirement — GDPR/SOC2 alignment
Multi-language Support (i18n) | Internationalisation | 800 | 1 | 50% | 4 |  |  | Could Have | Important for global expansion — later roadmap
API Rate Limiting & Throttling | Platform | 1500 | 2 | 80% | 1 |  |  | Should Have | Essential for API partnerships and scaling
Performance — Page Load < 2s | Performance | 5000 | 3 | 80% | 2.5 |  |  | Must Have | Core performance SLA — impacts all users
ⓘ Sort column G (RICE Score) descending to rank automatically. Higher RICE Score = Higher Priority.
RICE SUMMARY STATISTICS
Highest RICE Score
Lowest RICE Score
Average RICE Score
Total Must Have Items
Total Should Have Items
Total Could Have Items
Total Story/Effort Points

## MoSCoW Prioritization
[Your Company] — MoSCoW Prioritization Board
Must Have = Critical for launch ¦ Should Have = Important, not urgent ¦ Could Have = Nice to have ¦ Won't Have = Out of scope
Backlog Item / Feature | Epic / Theme | Owner | Sprint Target | MoSCoW | Rationale & Decision
MUST HAVE
User login & registration (email/password) | Auth Platform | Dev Team | Sprint 1 | Must Have | No product without authentication — launch blocker
Two-Factor Authentication (2FA) | Security | Dev Team | Sprint 4 | Must Have | Compliance and enterprise customer requirement
Dashboard — key metrics overview | Analytics | Dev Team | Sprint 3 | Must Have | Core value proposition — first screen users see
REST API — core CRUD endpoints | Platform | Dev Team | Sprint 2 | Must Have | All client apps depend on this — foundational
Audit log & activity history | Compliance | Dev Team | Sprint 5 | Must Have | GDPR + SOC2 requirement — legal obligation
Performance: pages load in < 2 seconds | Performance | Dev Team | Sprint 6 | Must Have | SLA commitment to enterprise clients
SHOULD HAVE
Real-time notifications (in-app + email) | Engagement | Dev Team | Sprint 7 | Should Have | High user value; workaround exists (polling)
Advanced search with filters | Discovery | Dev Team | Sprint 8 | Should Have | Power user feature — important but not launch-critical
Bulk CSV import for user data | Admin | Dev Team | Sprint 9 | Should Have | Requested by 60% of enterprise leads
Password reset via email | Auth Platform | Dev Team | Sprint 2 | Should Have | Expected but failure mode manageable (admin reset)
Role-based access control (RBAC) | Security | Dev Team | Sprint 6 | Should Have | Required for enterprise accounts — needed pre-GA
COULD HAVE
Dark mode UI theme | UX Enhancement | Design | Backlog | Could Have | Requested by some users; not a conversion driver
CSV export for reports | Reporting | Dev Team | Backlog | Could Have | Quick win but workaround exists — download raw data
Drag-and-drop interface | UX Enhancement | Design | Backlog | Could Have | Nice UX improvement; current UI is functional
Onboarding tutorial walkthrough | Onboarding | Dev Team | Backlog | Could Have | Reduces support load but not critical for launch
WON'T HAVE (This Release)
Mobile app (iOS/Android native) | Mobile | TBD | Q3 2026 | Won't Have | Roadmap item — post v1.0 expansion
AI-powered recommendations | Innovation | Data Team | Q4 2026 | Won't Have | Needs data volume first — premature optimisation
Multi-language support (i18n) | Internationalisation | Dev Team | Q3 2026 | Won't Have | International expansion planned for v2
Third-party marketplace integrations | Ecosystem | Dev Team | Q4 2026 | Won't Have | Partner agreements not yet finalised

## WSJF Calculator
[Your Company] — WSJF (Weighted Shortest Job First) Calculator
Formula: WSJF = Cost of Delay ÷ Job Size ¦ Cost of Delay = Business Value + Time Criticality + Risk Reduction
Score Scale: 1=Very Low ¦ 2=Low ¦ 4=Medium ¦ 8=High ¦ 16=Very High (Fibonacci-like)
Backlog Item | Business Value (1–16) | Time Criticality (1–16) | Risk Reduction (1–16) | Cost of Delay | Job Size (1–16) | WSJF Score | Priority Rank | Rationale
User Authentication — Login & Registration | 16 | 8 | 16 |  | 4 |  |  | No auth = no product. Maximum business value + risk.
Performance: Page Load < 2 seconds | 16 | 16 | 8 |  | 8 |  |  | SLA breach risk. Time-critical — enterprise clients waiting.
Two-Factor Authentication (2FA) | 8 | 16 | 16 |  | 8 |  |  | Compliance deadline Q2. High risk reduction if delayed.
Dashboard — KPI Summary View | 16 | 8 | 4 |  | 8 |  |  | Core value prop. Not urgent but very high business value.
Audit Log & Activity History | 8 | 16 | 16 |  | 4 |  |  | GDPR requirement. Small job but high criticality.
Advanced Search with Filters | 8 | 4 | 2 |  | 8 |  |  | Power user feature. Valuable but not urgent or risky.
Real-time Notifications | 8 | 4 | 2 |  | 4 |  |  | High value, small job — good WSJF despite lower urgency.
Bulk CSV Import | 4 | 8 | 4 |  | 4 |  |  | Unblocks enterprise onboarding — moderate across all.
Role-Based Access Control (RBAC) | 8 | 8 | 8 |  | 8 |  |  | Important for enterprise tier. Balanced across all factors.
Password Reset via Email | 8 | 4 | 2 |  | 2 |  |  | Small job. High business value despite low criticality.
CSV Export for Reports | 4 | 2 | 2 |  | 2 |  |  | Nice to have. Low cost of delay. Small but deprioritised.
Mobile App — iOS Native | 8 | 4 | 2 |  | 16 |  |  | High value but huge job. WSJF suffers from effort.
Dark Mode Theme | 2 | 1 | 1 |  | 4 |  |  | Low cost of delay. Cosmetic improvement only.
AI Recommendations | 4 | 2 | 4 |  | 16 |  |  | Interesting but very large job and uncertain value.
Multi-language Support | 4 | 4 | 2 |  | 8 |  |  | Future market — low current criticality.
ⓘ Sort column G (WSJF Score) descending to auto-rank. Higher WSJF = higher economic priority. Fill 'Priority Rank' column manually after sorting.

## Master Priority Board
[Your Company] — Master Backlog Priority Board
Combined view: RICE Score + WSJF Score + MoSCoW + Sprint Assignment — single source of truth for backlog ordering
Backlog Item | Category | RICE Score | WSJF Score | MoSCoW | Sprint Target | Status | Combined Priority | Decision Owner | Notes
User Authentication — Login & Registration | Core Platform | 15000 | 10 | Must Have | Sprint 1 | Committed | 1 — Critical | PO | Core launch requirement
Performance: Page Load < 2 seconds | Performance | 6000 | 5 | Must Have | Sprint 1 | Committed | 2 — Critical | PO + Architect | SLA compliance
Audit Log & Activity History | Compliance | 2933 | 10 | Must Have | Sprint 2 | Planned | 3 — Critical | PO + Legal | GDPR obligation
Two-Factor Authentication (2FA) | Security | 4667 | 5 | Must Have | Sprint 3 | Planned | 4 — High | PO + Security | Compliance deadline Q2
Dashboard — KPI Summary View | Analytics | 3200 | 3.5 | Must Have | Sprint 3 | Planned | 5 — High | PO | Core value prop
Password Reset via Email | Core Platform | 18000 | 7 | Should Have | Sprint 2 | Planned | 6 — High | PO | UX expectation
Real-time Notifications | Engagement | 5000 | 3.5 | Should Have | Sprint 4 | Planned | 7 — Medium | PO | Engagement driver
Role-Based Access Control (RBAC) | Security | 1467 | 3 | Should Have | Sprint 5 | Backlog | 8 — Medium | PO | Enterprise requirement
REST API — Core CRUD Endpoints | Platform | 10000 | 4 | Must Have | Sprint 1 | Committed | 9 — Medium | Architect | All clients depend on this
Advanced Search with Filters | Discovery | 2000 | 2 | Should Have | Sprint 6 | Backlog | 10 — Medium | PO | Power user feature
Bulk CSV Import | Admin | 1600 | 3 | Should Have | Sprint 6 | Backlog | 11 — Medium | PO | Unblocks enterprise onboarding
CSV Export for Reports | Reporting | 7200 | 3 | Could Have | Backlog | Backlog | 12 — Low | PO | Quick win — deprioritised
Dark Mode Theme | UX | 400 | 0.5 | Could Have | Backlog | Backlog | 13 — Low | Design Lead | Cosmetic only
Mobile App — iOS Native | Mobile | 750 | 0.875 | Won't Have | Q3 2026 | Backlog | 14 — Future | CPO | Post v1.0 roadmap
AI Recommendations | Innovation | 375 | 0.625 | Won't Have | Q4 2026 | Backlog | 15 — Future | CPO | Needs data volume first

## Instructions
HOW TO USE — Backlog Prioritization Calculator
OVERVIEW
Purpose | Combine three prioritization techniques (RICE, WSJF, MoSCoW) into one tool
Workflow | 1. Score all items in RICE tab → 2. Score in WSJF tab → 3. Assign MoSCoW → 4. Update Master Board
Update frequency | Review and update after each Sprint Review as backlog evolves
RICE CALCULATOR
Reach | Estimated number of users affected per quarter — use real data where available
Impact | 3=Massive, 2=High, 1=Medium, 0.5=Low, 0.25=Minimal on individual users
Confidence | 1.0=High certainty, 0.8=Medium, 0.5=Low — be honest; lower if assumptions unverified
Effort | Person-months required across all roles. 0.5=1 week, 1.0=1 month, 4.0=1 quarter
RICE Score | Auto-calculated: (Reach × Impact × Confidence) / Effort. Sort descending to rank.
WSJF CALCULATOR
Business Value | How much value does this deliver? Use Fibonacci-like: 1,2,4,8,16
Time Criticality | Is there a deadline? What is the cost of waiting? 1=no urgency → 16=critical
Risk Reduction | Does this reduce technical/business risk? 1=none → 16=major risk eliminated
Cost of Delay | Auto-calculated: Business Value + Time Criticality + Risk Reduction
Job Size | Relative effort. 1=tiny, 2=small, 4=medium, 8=large, 16=very large feature
WSJF Score | Cost of Delay / Job Size. Higher = sequence this first. Sort descending.
MOSCOW BOARD
Must Have | Launch blocker. Product cannot ship without this. Non-negotiable.
Should Have | High value, not urgent. Include if time allows — workaround exists.
Could Have | Nice to have. Included only if budget and time remaining.
Won't Have | Explicitly out of scope for this release. Document the decision.
MASTER PRIORITY BOARD
Purpose | Single source of truth — combines all scoring methods and sprint assignments
Combined Priority | Use your judgement combining RICE + WSJF + MoSCoW + stakeholder context
Status | Committed = in Sprint Backlog ¦ Planned = next 2 sprints ¦ Backlog = ordered but not scheduled
Decision Owner | Who made the prioritization decision — for accountability and audit trail
BEST PRACTICES
Don't over-rely on scores | Scores inform decisions — they don't make them. Use judgement too.
Involve the team | Refinement sessions: team estimates Effort (RICE & WSJF); PO scores Value
Review monthly | Priorities change — a stale priority score is worse than no score
Document decisions | 'Why' is as important as 'what' — fill in the Rationale column always