## Change Request Log
CHANGE REQUEST LOG – [YOUR COMPANY]
Project: Digital Transformation ¦ PM: [Your Name] ¦ Updated: 2026-03-30
CR ID | Date Raised | Raised By | Title | Description | Category | Priority | Schedule Impact | Cost Impact | Risk Level | Decision | Decision By | Impl. Date | Status | Notes
CR-001 | 2026-01-15 | James Worthington | Add executive reporting dashboard | New C-suite requirement for real-time project visibility dashboard | Scope | High | 2 weeks | £5,000 | Medium | Approved | [Your Name] | 2026-02-15 | Complete | Dashboard delivered on time and signed off
CR-002 | 2026-01-20 | Ahmed Al-Rashid | Upgrade API version from v2 to v3 | API provider ending v2 support in March 2026. Mandatory upgrade required. | Technical | High | 1 week | £2,000 | High | Approved | [Your Name] | 2026-02-01 | Complete | Completed without issues
CR-003 | 2026-02-01 | Layla Mansour | Additional automated test coverage for payments | Risk reduction following P1 defect found in UAT. Requires regression test build. | Quality | High | 3 days | £3,000 | Medium | Approved | [Your Name] | 2026-02-20 | Complete | Coverage increased from 60% to 85%
CR-004 | 2026-02-10 | Finance Director | Monthly financial reconciliation report | Finance team requirement missed in original scope discovery. High business value. | Scope | Medium | 1 week | £4,000 | Low | Approved | [Your Name] | 2026-03-01 | In Progress | Development 70% complete
CR-005 | 2026-02-15 | Legal Officer | GDPR consent management module | Regulatory compliance requirement identified in legal review. Non-negotiable. | Compliance | Critical | 3 weeks | £15,000 | Critical | Approved | James Worthington | 2026-03-15 | In Progress | Legal requirements fully documented
CR-006 | 2026-02-20 | Operations Manager | Bulk data import tool for legacy migration | Operations team needs tool to migrate 50,000 records from legacy system to new platform. | Scope | High | 2 weeks | £8,000 | Medium | Approved | [Your Name] | 2026-04-01 | In Progress | Technical design complete
CR-007 | 2026-02-25 | Sales Director | Salesforce CRM bi-directional integration | Sales team needs two-way sync between new platform and Salesforce CRM. | Technical | High | 3 weeks | £12,000 | High | Approved | James Worthington | 2026-04-15 | In Progress | API design agreed
CR-008 | 2026-03-01 | Ahmed Al-Rashid | Add Redis caching layer for performance | Performance testing shows dashboard load times exceed 5-second threshold under load. | Technical | High | 1 week | £3,500 | Medium | Approved | [Your Name] | 2026-03-20 | Complete | Load times now under 1.2 seconds
CR-009 | 2026-03-05 | HR Director | Staff training progress dashboard | HR needs visibility of training completion across all departments in real-time. | Scope | Medium | 1 week | £2,500 | Low | Approved | [Your Name] | 2026-04-10 | In Progress | Design in review
CR-010 | 2026-03-08 | QA Lead | Performance testing for 500 concurrent users | Current load testing only covers 100 users. Production expects up to 500. | Quality | High | 1 week | £4,000 | High | Pending | Pending | TBC | Pending | Awaiting sign-off from Tech Lead
CR-011 | 2026-03-10 | Marketing Lead | Custom branded login page | Marketing request for branded login page with company logo and colour scheme. | Scope | Low | 2 days | £800 | Low | Deferred | [Your Name] | TBC | Deferred | Deferred to Phase 2
CR-012 | 2026-03-12 | Ahmed Al-Rashid | Dark mode for UI | Developer team request for dark mode theme to reduce eye strain. | Scope | Low | 1 week | £2,000 | Low | Deferred | [Your Name] | TBC | Deferred | Phase 2 backlog
CR-013 | 2026-03-14 | Legal Officer | Data residency clause — UAE-only storage | Regulatory update requires all customer data to be stored only in UAE data centres. | Compliance | Critical | 2 weeks | £7,000 | Critical | Pending | Pending | TBC | Pending | Legal review in progress
CR-014 | 2026-03-18 | Finance Director | Automated VAT calculation in invoices | UAE VAT regulation requires 5% calculation on all B2B invoices generated by the system. | Compliance | High | 1 week | £3,000 | High | Approved | James Worthington | 2026-04-05 | In Progress | Tax module spec agreed
CR-015 | 2026-03-20 | Sales Director | Bulk email notification system | Sales needs ability to send system notifications to client groups for campaign updates. | Scope | Medium | 2 weeks | £6,000 | Medium | Pending | Pending | TBC | Pending | Business case being reviewed
CR-016 | 2026-03-22 | Rania Farouq | Infrastructure auto-scaling configuration | Current infra does not auto-scale. Required for go-live to handle peak load. | Technical | Critical | 1 week | £5,000 | High | Approved | James Worthington | 2026-04-08 | In Progress | Config being built
CR-017 | 2026-03-24 | Bashir Suleiman | Enhanced search with full-text indexing | Current search is basic. Business analysts need full-text search across all records. | Scope | Medium | 2 weeks | £5,500 | Low | Rejected | [Your Name] | N/A | Rejected | Rejected — out of scope for Phase 1
CR-018 | 2026-03-25 | Operations Manager | Mobile responsive design for field teams | Operations field teams access on mobile. Current responsive design fails below 768px. | Technical | High | 2 weeks | £7,000 | Medium | Pending | Pending | TBC | Pending | Impact assessment underway
CR-019 | 2026-03-26 | Ahmed Al-Rashid | API rate limit increase from 100 to 500 req/min | Partner integrations require higher throughput. Current limit causing integration failures. | Technical | High | 3 days | £1,500 | Low | Approved | [Your Name] | 2026-04-02 | In Progress | Infrastructure config in progress
CR-020 | 2026-03-28 | James Worthington | Go-live date moved from Apr 15 to Apr 22 | Risk assessment recommends 1-week delay for additional testing and stakeholder readiness. | Schedule | Critical | 1 week delay | £0 | High | Pending | Pending | TBC | Pending | Executive decision required by 2026-04-01

## Impact Template
CHANGE REQUEST IMPACT ASSESSMENT TEMPLATE
1. CHANGE SUMMARY
Title:
Date:
Category:
2. BUSINESS JUSTIFICATION
Why is this change needed?
Expected Benefit:
Consequence of NOT changing:
3. IMPACT ANALYSIS
Impact Area | Baseline | Impact Description | Magnitude (H/M/L) | Mitigation
Schedule
Cost
Scope
Quality
Risk
Resource
Stakeholders
4. OPTIONS CONSIDERED
Option A:
Option B:
Recommendation:
5. APPROVAL SIGN-OFFS
Project Manager:
Executive Sponsor:
Technical Lead:
Finance Lead:

## CR Dashboard
CHANGE REQUEST DASHBOARD
Summary as of 2026-03-30
BY STATUS
Complete | 5 | Critical | 4
In Progress | 8 | High | 10
Pending | 5 | Medium | 5
Deferred | 2 | Low | 2
Rejected | 1
Total | 21
MONTHLY VOLUME (2026)
January | 2 | Scope | 7
February | 6 | Technical | 7
March | 12 | Compliance | 3
April | 0 | Quality | 2
May | 0 | Schedule | 1
June | 0 | Other | 1