## Company OKRs
OKR TRACKER – [YOUR COMPANY] ¦ Q2 2026
Vision: To be the leading digital transformation partner in the region
Level | Objective | Key Result | Owner | Target | Current | Progress % | Confidence | Status | Notes
Company | Achieve £2M ARR by end of Q2 2026 | Onboard 15 new enterprise clients | Sales Director | 15 | 8 | 53 | 6 | On Track
|  | Increase average deal size from £85K to £120K | Sales Director | 120000 | 95000 | 63 | 7 | On Track
|  | Reduce sales cycle from 45 to 30 days | Sales Ops | 30 | 38 | 47 | 5 | At Risk
Company | Build a world-class delivery team | Hire 8 senior engineers by June 2026 | HR Director | 8 | 5 | 63 | 7 | On Track
|  | Achieve 90% sprint goal completion rate | Head of Eng | 90 | 82 | 91 | 6 | On Track
|  | Reduce team attrition to under 5% per quarter | HR Director | 5 | 7 | 0 | 4 | Behind
Company | Establish [Your Company] as a thought leader in the region | Publish 12 client case studies | Marketing | 12 | 4 | 33 | 6 | At Risk
|  | Achieve NPS of 75+ | CX Lead | 75 | 68 | 91 | 7 | On Track
|  | Secure 3 speaking slots at industry events | Marketing | 3 | 1 | 33 | 5 | At Risk

## Team OKRs
TEAM OKRs – Q2 2026
Engineering ¦ Sales ¦ Operations teams
Level | Objective | Key Result | Owner | Target | Current | Progress % | Confidence | Status | Notes
Engineering | Ship features faster and with higher quality | Reduce average feature cycle time from 3 weeks to 10 days | Head of Eng | 10 | 14 | 57 | 6 | At Risk
|  | Achieve 85% automated test coverage across core modules | QA Lead | 85 | 71 | 84 | 7 | On Track
|  | Zero P1 defects in production for 8 consecutive weeks | Tech Lead | 8 | 4 | 50 | 7 | On Track
Sales | Grow pipeline and improve conversion | Generate £1.2M in qualified pipeline by end of quarter | Sales Manager | 1200000 | 820000 | 68 | 7 | On Track
|  | Improve lead-to-proposal conversion from 35% to 50% | Sales Director | 50 | 41 | 82 | 6 | On Track
|  | Retain 100% of enterprise clients with NPS > 70 | Account Mgr | 100 | 95 | 95 | 8 | On Track
Operations | Build operational excellence and reduce costs | Reduce operational cost per delivery by 15% | Ops Director | 15 | 8 | 53 | 6 | At Risk
|  | Implement end-to-end project tracking for all clients | PM Lead | 100 | 60 | 60 | 6 | At Risk
|  | Complete ISO 27001 readiness assessment | Compliance Lead | 100 | 30 | 30 | 5 | Behind

## Check-In Log
OKR CHECK-IN LOG – Q2 2026
Date | Team | Objective (Short) | Key Result Update | Progress % | Confidence | Blockers | Support Needed | Updated By
2026-04-04 | Company | Achieve £2M ARR | Onboarded 2 new clients this week, total 8 of 15 | 53 | 6 | Long procurement cycles in public sector | Introduce public sector contract template | [Your Name]
2026-04-04 | Engineering | Ship features faster | Cycle time now 14 days, down from 18 last week | 57 | 7 | PR review queue growing | Need 1 dedicated reviewer per sprint | Ahmed Al-Rashid
2026-04-04 | Operations | Reduce cost per delivery | Identified 3 process efficiencies, implementing 1 | 40 | 5 | Resource conflict with Project Beta | Prioritisation decision needed from leadership | Yusuf Al-Amin
2026-04-11 | Company | Build delivery team | 5 engineers hired, 3 still in final rounds | 63 | 7 | Notice periods longer than expected | Fast-track notice buy-out for 2 candidates | HR Director
2026-04-11 | Sales | Grow pipeline | Pipeline now at £820K. 2 proposals submitted this week | 68 | 7 | None this week |  | Sales Director
2026-04-18 | Company | Thought leadership | Case study 4 published. 2 more in review | 33 | 6 | Client approval delays | Template for faster sign-off | Marketing Lead
2026-04-18 | Engineering | Zero P1 defects | 4 consecutive clean weeks achieved | 50 | 8 |  | Continue current quality practices | QA Lead
2026-04-25 | Company | Achieve £2M ARR | Deal size average now £95K, up from £85K | 63 | 7 | Two deals stalled at legal stage | Legal fast-track process for enterprise deals | Sales Director
2026-04-25 | Operations | ISO readiness | Assessment 30% complete. Vendor selected | 30 | 5 | Internal resource constraint | Dedicated 20% of 1 BA to this initiative | Ops Director
2026-05-02 | Company | Build delivery team | 6th engineer started today. Strong start | 75 | 8 |  |  | HR Director
2026-05-02 | Sales | Conversion rate | Conversion now at 41%, improving from 35% | 82 | 7 | Proposal quality varies by sales rep | Sales enablement coaching needed | Sales Manager
2026-05-09 | Company | NPS 75+ | NPS now 68, up from 62 last quarter | 91 | 7 | 2 unhappy clients need attention | CX team involvement in at-risk accounts | CX Lead

## OKR Guide
OKR WRITING GUIDE – [YOUR COMPANY]
WHAT IS AN OKR?
OKRs (Objectives and Key Results) are a goal-setting framework that connects ambitious goals (Objectives) to measurable proof of achievement (Key Results). Used by Google, Intel, Spotify and thousands of companies worldwide.
WRITING OBJECTIVES
• Qualitative and inspirational — it should motivate the team
• Achievable within one quarter (or one year for company OKRs)
• Memorable — a team member should be able to recall it without looking
• Formula: "We will [action] so that [outcome]"
WRITING KEY RESULTS
• Quantitative — always has a number. If no number, it is a task not a KR
• Formula: "[Verb] [metric] from X to Y by [date]"
• 2-5 Key Results per Objective (3 is optimal)
• Avoid output metrics (meetings held, reports sent) — focus on outcomes
GRADING GUIDE
0.7 (70%) = Stretch success. If you always hit 1.0, your targets are too easy.
0.4-0.6 = Learning zone. Understand why and plan recovery.
0.0-0.3 = Missed. Deep dive required. What needs to change?
COMMON MISTAKES
• Too many OKRs (3 company, 3-4 team is the maximum)
• Copying last quarter's OKRs without reflection
• Linking OKR grades to performance reviews (kills honesty)
• No weekly check-ins (OKRs die without regular attention)
CENTAUR OKR CALENDAR
Week 1 of Quarter: Set OKRs (company first, then teams)
Weekly: 15-min team check-in — update progress and confidence scores
Mid-quarter: Full OKR review — adjust targets if needed
Last week of quarter: Grade OKRs and capture learnings