## Risk Register
PROJECT RISK REGISTER – [YOUR COMPANY]
Project: [Project Name] ¦ PM: [Your Name] ¦ Date: 2026-03-30 ¦ Version: 1.0
Risk ID | Category | Risk Description | Probability (1-5) | Impact (1-5) | Risk Score | Risk Level | Owner | Response | Mitigation Actions | Contingency Plan | Status
R-001 | Technical | Key developer leaves mid-project | 3 | 4 | 12 | HIGH | PM Name | Mitigate | Cross-train team members and document all key processes | Identify and brief a backup contractor | Open
R-002 | Resource | Budget overrun due to scope creep | 4 | 4 | 16 | CRITICAL | Finance Lead | Mitigate | Enforce change control process and weekly budget reviews | Request additional budget from executive sponsor | Open
R-003 | Schedule | Third-party API integration delayed | 3 | 3 | 9 | MEDIUM | Tech Lead | Mitigate | Engage vendor early and run parallel development tracks | Build mock API layer for development continuity | Open
R-004 | Stakeholder | Key sponsor unavailable for decisions | 2 | 4 | 8 | MEDIUM | PM Name | Mitigate | Establish RACI and delegate approval authority | Escalate to executive sponsor immediately | Monitoring
R-005 | Security | Data breach via insecure API endpoint | 2 | 5 | 10 | HIGH | Security Lead | Mitigate | Security code review and penetration testing | Activate incident response and notification plan | Open
R-006 | Compliance | GDPR non-compliance in data handling | 2 | 5 | 10 | HIGH | Legal Lead | Avoid | Engage DPO early and review all data flows | Engage regulatory legal counsel | Open
R-007 | Vendor | Cloud provider outage affects production | 2 | 4 | 8 | MEDIUM | DevOps Lead | Transfer | Multi-region deployment and automated failover | Activate DR plan and switch to backup region | Monitoring
R-008 | Resource | Key tester leaves during UAT phase | 3 | 3 | 9 | MEDIUM | QA Lead | Mitigate | Document all test cases and cross-train backup tester | Contract specialist UAT resource | Open
R-009 | Technical | Database migration causes data loss | 2 | 5 | 10 | HIGH | Tech Lead | Mitigate | Full backup before migration and dry run in staging | Roll back to previous stable version | Open
R-010 | Schedule | Requirements change late in development | 4 | 3 | 12 | HIGH | BA Lead | Mitigate | Strict change control process and requirements freeze | Negotiate scope reduction or timeline extension | Open
R-011 | Resource | Team capacity below sprint commitments | 3 | 3 | 9 | MEDIUM | Scrum Master | Mitigate | Capacity planning and sprint velocity tracking | Re-prioritise backlog and remove lower-priority items | Open
R-012 | Technical | Infrastructure provisioning delayed | 2 | 3 | 6 | MEDIUM | DevOps Lead | Mitigate | Infrastructure-as-code templates pre-approved | Use existing shared environment temporarily | Open
R-013 | Stakeholder | Low user adoption of new system | 3 | 4 | 12 | HIGH | PM Name | Mitigate | Change management programme and early user involvement | Extended hyper-care support post go-live | Open
R-014 | Technical | Integration testing gaps causing defects | 3 | 3 | 9 | MEDIUM | QA Lead | Mitigate | Automated integration test suite and regression testing | Extend testing phase before release | Open
R-015 | External | Regulatory change impacts solution design | 1 | 5 | 5 | MEDIUM | Legal Lead | Monitor | Regular regulatory monitoring and monthly review | Emergency design sprint to address changes | Open

## Dashboard
RISK DASHBOARD – [YOUR COMPANY]
Summary of project risks by level
Risk Level | Count | % of Total | Severity
CRITICAL | 3 | 20.0%
HIGH | 4 | 26.7%
MEDIUM | 6 | 40.0%
LOW | 2 | 13.3%
TOTAL | 15 | 100%
SCORING GUIDE
Score 1-4 | LOW | Risk is minor. Monitor only.
Score 5-9 | MEDIUM | Risk needs mitigation plan.
Score 10-14 | HIGH | Requires immediate mitigation.
Score 15-25 | CRITICAL | Executive escalation required.

## Instructions
RISK REGISTER – USAGE GUIDE
WHAT IS THIS?
This register helps you identify, assess, monitor and manage project risks throughout the project lifecycle.
PROBABILITY SCALE
1 = Very Low: Unlikely (<10%)
2 = Low: Possible (10-30%)
3 = Medium: Likely (30-50%)
4 = High: Very Likely (50-70%)
5 = Very High: Almost Certain (>70%)
IMPACT SCALE
1 = Minimal: Minor inconvenience, easily managed
2 = Minor: Some disruption, manageable
3 = Moderate: Significant impact on schedule/cost
4 = Major: Serious impact, requires escalation
5 = Catastrophic: Project failure or major loss
RESPONSE STRATEGIES
AVOID: Change plan to eliminate the risk entirely
MITIGATE: Take action to reduce probability or impact
TRANSFER: Shift risk to third party (insurance, contract)
ACCEPT: Acknowledge risk and monitor — no action needed
RISK SCORE = Probability x Impact (1-25 scale)