## RAG Dashboard
PROJECT STATUS REPORT – [YOUR COMPANY]
Reporting Period: March 2026 ¦ PM: [Your Name] ¦ Project: Digital Transformation Programme
SECTION A: OVERALL PROJECT STATUS
OVERALL RAG STATUS |  | AMBER |  | Last Updated: | 2026-03-30
Project is progressing with some areas at risk. Development is on track. Infrastructure security review is blocking deployment timeline. Stakeholder sponsor unavailable — escalation raised. Commercial activities on track.
SECTION B: WORKSTREAM STATUS
Workstream | RAG Status | Previous Period | Trend | Comments
Design | Green | Green | Stable | All design assets signed off. Design system documentation 95% complete.
Development | Green | Amber | Improving | Sprint 8 of 12 complete. Velocity at 45 points. All P1 features delivered.
Testing | Amber | Amber | Stable | UAT environment issues resolved. 18% of test cases outstanding. On track for UAT sign-off.
Infrastructure | Amber | Red | Improving | Cloud configured. Security review sign-off still pending from IT team.
Stakeholder Engagement | Red | Amber | Worsening | Executive sponsor unavailable for 3 weeks. Key decisions blocked. Escalation raised.
Commercial | Green | Green | Stable | Contract amendments signed. Invoicing on track. No budget concerns.
SECTION C: KEY MILESTONES
Milestone | Planned Date | Forecast Date | Actual Date | Status | Owner
Requirements Sign-off | 2026-01-31 | 2026-01-31 | 2026-01-31 | Complete | BA Lead
Design Completion | 2026-02-15 | 2026-02-15 | 2026-02-14 | Complete | Design Lead
Development Sprints 1-4 Complete | 2026-02-28 | 2026-02-28 | 2026-02-28 | Complete | Tech Lead
UAT Environment Ready | 2026-03-10 | 2026-03-10 | 2026-03-10 | Complete | DevOps Lead
UAT Commencement | 2026-03-10 | 2026-03-13 | — | In Progress | QA Lead
Security Penetration Test | 2026-03-20 | 2026-04-05 | — | At Risk | Security Lead
UAT Sign-off | 2026-03-31 | 2026-04-07 | — | At Risk | PM
Go-Live | 2026-04-15 | 2026-04-22 | — | At Risk | PM
SECTION D: TOP RISKS & OPEN ISSUES
Risk | Probability | Impact | Level | Owner
Executive sponsor unavailable — decisions blocked | High | High | CRITICAL | PM
Security penetration test delayed by IT review | Medium | High | HIGH | Security Lead
UAT test cases not complete | Medium | High | HIGH | QA Lead
Infrastructure auto-scaling not yet configured | Low | High | HIGH | DevOps Lead
Data migration script not tested under load | Low | High | MEDIUM | Tech Lead
OPEN ISSUES
Issue | Raised By | Date | Priority | Owner / Status
Executive sponsor unreachable — 3 critical decisions blocked | James Worthington | 2026-03-20 | Critical | PM — Escalated to board. Interim decision-maker requested.
IT security sign-off 2 weeks behind schedule | IT Security Lead | 2026-03-18 | High | DevOps Lead — Weekly chasing. Senior IT Director engaged.
UAT environment performance degradation during load test | QA Lead | 2026-03-25 | High | Tech Lead — Root cause identified. Fix in progress.
SECTION E: FINANCIALS
Budget Category | Budget (£) | Forecast (£) | Actual to Date (£) | Variance (£) | RAG
Development | 120000 | 125000 | 78000 | -5000 | Amber
Infrastructure | 35000 | 38000 | 22000 | -3000 | Amber
Testing & QA | 25000 | 25000 | 14000 | 0 | Green
Project Management | 40000 | 40000 | 27000 | 0 | Green
Contingency (10%) | 22000 | 22000 | 0 | 22000 | Green
TOTAL | 242000 | 250000 | 141000 | 14000
SECTION F: DECISIONS REQUIRED
Decision Required | Owner | Required By | Priority | Notes
Confirm revised go-live date of 22 April 2026 | James Worthington | 2026-04-01 | Critical | Requires board confirmation. PM has prepared impact assessment and rationale.
Approve additional £8,000 for security testing | Finance Director | 2026-04-03 | High | Security consultancy required due to IT team availability constraints.
Authorise additional QA resource for final 2 weeks | [Your Name] | 2026-04-05 | High | 2 additional testers needed to close UAT backlog safely before go-live.
Sign off on data residency architecture approach | Legal Officer | 2026-04-08 | Critical | Legal requirement for UAE-only data storage. Technical design prepared.

## History
RAG STATUS HISTORY – DIGITAL TRANSFORMATION PROGRAMME
Month | Overall RAG | Schedule RAG | Cost RAG | Quality RAG | Risk RAG | Key Events / Notes
Jan 2026 | Green | Green | Green | Green | Green | Project kicked off. Requirements completed on time. Strong start.
Feb 2026 | Green | Green | Green | Green | Amber | First technical risk identified (API upgrade). Managed well.
Mar 2026 | Amber | Amber | Amber | Green | Red | Sponsor unavailability blocking decisions. Security review delayed. UAT commencement delayed by 3 days.
Apr 2026 | [5 empty] | (Forecast) Expect recovery if go-live delay approved and sponsor returns.
May 2026
Jun 2026

## Guide
RAG STATUS GUIDE & REPORTING INSTRUCTIONS
GREEN — On Track | Project is progressing as planned. No significant risks or issues. Normal monitoring.
AMBER — At Risk | Risk or issue present but manageable. Action plan in place. Escalation may be required.
RED — Critical Issue | Significant risk or issue requiring immediate attention. Executive escalation required.
Weekly | Project team — internal status update and action tracking
Bi-weekly | Sponsor — executive summary with overall RAG and key decisions
Monthly | Steering committee — full RAG report including financials
Amber → Red | When: no clear path to resolution within 5 working days; cost/schedule impact > 10%; executive decision required
Red → Escalate | When: project cannot continue without board/executive intervention; contractual breach risk
Risks | Potential future events that could impact the project negatively. Tracked in Risk Register.
Assumptions | Conditions assumed to be true for planning purposes. Must be validated regularly.
Issues | Problems that are currently affecting the project. Active management required.
Dependencies | Activities or decisions outside the team's control that the project relies upon.