## Capacity Overview
RESOURCE & CAPACITY PLANNER – [YOUR COMPANY]
Plan: 01 Apr – 26 May 2026 (8 Weeks) ¦ PM: [Your Name]
Resource | Role | W1 (5 days) | W2 (5 days) | W3 (5 days) | W4 (5 days) | W5 (5 days) | W6 (5 days) | W7 (5 days) | W8 (5 days) | Total Available | Total Allocated | Utilisation %
Ahmed Al-Rashid | Senior Developer | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 40 | 38 | 95.0%
Sara Khalid | Senior Developer | 5 | 5 | 3 | 5 | 5 | 5 | 5 | 5 | 38 | 34 | 89.5%
Omar Hassan | Mid Developer | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 40 | 36 | 90.0%
Fatima Zahra | Mid Developer | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 39 | 34 | 87.2%
Khalid Ibrahim | Junior Developer | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 40 | 28 | 70.0%
Nour Al-Din | Junior Developer | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 39 | 26 | 66.7%
Layla Mansour | QA Engineer | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 40 | 38 | 95.0%
Tariq Osman | QA Engineer | 5 | 5 | 5 | 3 | 5 | 5 | 5 | 5 | 38 | 30 | 78.9%
Rania Farouq | DevOps Engineer | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 40 | 32 | 80.0%
Yusuf Al-Amin | Scrum Master | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 40 | 40 | 100.0%
Amira Nidal | UX Designer | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 35 | 20 | 57.1%
Bashir Suleiman | Business Analyst | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 40 | 38 | 95.0%
TOTAL |  | 60 | 59 | 58 | 58 | 59 | 60 | 60 | 55 | 469 | 394 | 84.0%

## Project Allocation
PROJECT ALLOCATION – [YOUR COMPANY]
Allocation of resources across active projects (days per 8-week period)
Resource | Role | Project Alpha | Project Beta | Project Gamma | BAU & Support | Total Allocated | Available | Over/Under | Notes
Ahmed Al-Rashid | Senior Developer | 20 | 10 | 0 | 8 | 38 | 40 | 2
Sara Khalid | Senior Developer | 15 | 12 | 0 | 7 | 34 | 38 | 4
Omar Hassan | Mid Developer | 18 | 0 | 12 | 6 | 36 | 40 | 4
Fatima Zahra | Mid Developer | 14 | 0 | 15 | 5 | 34 | 39 | 5
Khalid Ibrahim | Junior Developer | 12 | 0 | 10 | 6 | 28 | 40 | 12
Nour Al-Din | Junior Developer | 10 | 0 | 12 | 4 | 26 | 39 | 13
Layla Mansour | QA Engineer | 20 | 10 | 0 | 8 | 38 | 40 | 2
Tariq Osman | QA Engineer | 12 | 0 | 12 | 6 | 30 | 38 | 8
Rania Farouq | DevOps Engineer | 15 | 10 | 0 | 7 | 32 | 40 | 8
Yusuf Al-Amin | Scrum Master | 20 | 10 | 10 | 0 | 40 | 40 | 0
Amira Nidal | UX Designer | 15 | 0 | 0 | 5 | 20 | 35 | 15
Bashir Suleiman | Business Analyst | 18 | 12 | 0 | 8 | 38 | 40 | 2

## Sprint Capacity
SPRINT CAPACITY PLANNING
Team Member | Role | Sprint Days | Meetings (d) | Dev Capacity | Committed Pts | Completed Pts | Efficiency %
Ahmed Al-Rashid | Senior Dev | 10 | 1 | 9 | 48 | 45 | 94%
Sara Khalid | Senior Dev | 10 | 1.5 | 8.5 | 42 | 40 | 95%
Omar Hassan | Mid Dev | 10 | 1 | 9 | 38 | 36 | 95%
Fatima Zahra | Mid Dev | 10 | 1.5 | 8.5 | 35 | 33 | 94%
Khalid Ibrahim | Junior Dev | 10 | 1 | 9 | 22 | 20 | 91%
Layla Mansour | QA Eng | 10 | 1.5 | 8.5 | 0 | 0 | N/A
Rania Farouq | DevOps | 10 | 1 | 9 | 0 | 0 | N/A
Yusuf Al-Amin | Scrum Master | 10 | 4 | 6 | 0 | 0 | N/A

## Leave Calendar
LEAVE CALENDAR 2026 – [YOUR COMPANY]
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
Ahmed Al-Rashid | Apr: 5; Jul: 10; Aug: 5; Dec: 5 | 25
Sara Khalid | Feb: 3; Jun: 5; Aug: 10; Oct: 5 | 23
Omar Hassan | Jan: 5; May: 5; Aug: 5; Sep: 5 | 20
Fatima Zahra | Mar: 3; Jul: 5; Aug: 10; Nov: 5 | 23
Khalid Ibrahim | Jun: 5; Jul: 5; Aug: 5 | 15
Nour Al-Din | Apr: 5; Aug: 5; Sep: 5; Dec: 5 | 20
Layla Mansour | Feb: 5; Jul: 10; Aug: 5; Oct: 5 | 25
Tariq Osman | Mar: 5; Jun: 5; Aug: 5; Nov: 5 | 20
Rania Farouq | Jan: 5; May: 5; Jul: 5; Aug: 5; Dec: 5 | 25
Yusuf Al-Amin | Apr: 5; Jul: 5; Aug: 10; Oct: 5 | 25
Amira Nidal | Feb: 5; May: 5; Aug: 10; Nov: 5 | 25
Bashir Suleiman | Jan: 5; Jun: 5; Aug: 5; Sep: 5; Dec: 5 | 25
TOTAL LEAVE DAYS | 15 | 13 | 8 | 15 | 15 | 20 | 40 | 80 | 15 | 15 | 15 | 20 | 271