## Retro Log
SPRINT RETROSPECTIVE TRACKER – [Your Company]
Track learnings and actions from every sprint retrospective
Sprint # | Sprint Dates | Facilitator | What Went Well | What Could Improve | Actions Count | Owner | Status | Mood (1-5) | Notes
1 | 01 Mar – 14 Mar | [Your Name] | Great team collaboration on API module. Standup energy high. | Standup often runs 30+ mins. Need timeboxing. | 3 | Scrum Master | Complete | 4 | Good start to Q1
2 | 15 Mar – 28 Mar | Sarah Ahmed | Early delivery of login feature. Good pair programming. | Insufficient testing time at sprint end creates crunch. | 2 | QA Lead | Complete | 3 | Testing bottleneck confirmed
3 | 29 Mar – 11 Apr | [Your Name] | Automated CI/CD pipeline working well. Faster deployments. | Technical debt accumulating in payments module. | 4 | Tech Lead | In Progress | 4 | Tech debt spike approved for Sprint 5
4 | 12 Apr – 25 Apr | Ahmed Al-Rashid | New junior onboarded smoothly. Good buddy system. | Cross-team dependencies blocking 2 stories mid-sprint. | 3 | PM Name | In Progress | 3 | Dependency tracking process needed
5 | 26 Apr – 09 May | [Your Name] | Technical debt sprint successful. Codebase cleaner. | Sprint planning sessions too long (avg 4 hours). | 2 | Scrum Master | In Progress | 4 | Planning refinement in progress
6 | 10 May – 23 May | Sarah Ahmed | Demo well received by client. Great preparation by team. | Documentation consistently skipped under pressure. | 3 | Tech Lead | Not Started | 4 | Doc standard to be agreed
7 | 24 May – 06 Jun | Ahmed Al-Rashid | Retrospective format change (sailboat) refreshed engagement. | Communication gaps between backend and frontend teams. | 2 | PM Name | Not Started | 4 | Cross-team daily sync proposed
8 | 07 Jun – 20 Jun | [Your Name] | Deployment frequency increased to twice per sprint. | Stakeholder demo prep taking too much dev time. | 2 | Product Owner | Not Started | 5 | Pre-demo checklist to be created
9 | 21 Jun – 04 Jul | Sarah Ahmed | Team NPS survey result: 4.2/5 — highest ever. | Sprint goal too vague — hard to assess success. | 3 | Scrum Master | Not Started | 5 | SMART sprint goal template created
10 | 05 Jul – 18 Jul | [Your Name] | All sprint goals met for 3rd consecutive sprint! | Onboarding documentation still incomplete for new hires. | 2 | HR + Tech Lead | Not Started | 5 | Onboarding wiki sprint planned

## Action Tracker
RETROSPECTIVE ACTION TRACKER – [Your Company]
Track all actions raised in sprint retrospectives to completion
Action ID | Sprint | Action | Owner | Priority | Due Date | Status | Outcome | Category
ACT-001 | 1 | Implement 15-minute standup timebox | Scrum Master | H | 2026-03-21 | Complete | Standup now averages 12 mins | Process
ACT-002 | 1 | Create cross-training schedule for API module | Tech Lead | H | 2026-03-28 | Complete | All devs trained on API layer | Technical
ACT-003 | 1 | Document API integration patterns | Ahmed Al-Rashid | M | 2026-03-28 | Complete | Wiki page created and reviewed | Technical
ACT-004 | 2 | Add testing buffer to sprint planning (last 2 days) | Scrum Master | H | 2026-04-04 | Complete | Buffer adopted. Sprint 3 testing improved. | Process
ACT-005 | 2 | Create test-ready definition of done | QA Lead | H | 2026-04-04 | Complete | DoD updated and team agreed | Quality
ACT-006 | 3 | Schedule payments module tech debt spike | Tech Lead | H | 2026-04-25 | Complete | Spike completed in Sprint 5 | Technical
ACT-007 | 3 | Create dependency tracking board in Jira | PM Name | M | 2026-04-18 | In Progress | Board created, team training pending | Process
ACT-008 | 3 | Define cross-team dependency SLA | PM Name | M | 2026-04-25 | In Progress | Draft SLA shared for review | Process
ACT-009 | 4 | Set up daily 10-min cross-team sync | PM Name | H | 2026-05-02 | In Progress | Sync running. Format being refined. | Communication
ACT-010 | 4 | Map all active inter-team dependencies | BA Lead | M | 2026-05-09 | Not Started |  | Process
ACT-011 | 5 | Redesign sprint planning to 2x 90-min sessions | Scrum Master | M | 2026-05-16 | In Progress | Piloting new format in Sprint 6 | Process
ACT-012 | 5 | Create sprint planning agenda template | Scrum Master | L | 2026-05-23 | Not Started |  | Process
ACT-013 | 6 | Agree documentation standard with team | Tech Lead | H | 2026-05-30 | Not Started |  | Technical
ACT-014 | 6 | Add documentation to sprint definition of done | QA Lead | H | 2026-06-06 | Not Started |  | Quality
ACT-015 | 6 | Create automated doc generation from code comments | Ahmed Al-Rashid | M | 2026-06-20 | Not Started |  | Technical
ACT-016 | 7 | Schedule weekly backend-frontend alignment call | PM Name | M | 2026-06-13 | Not Started |  | Communication
ACT-017 | 7 | Create API contract documentation template | Tech Lead | M | 2026-06-20 | Not Started |  | Technical
ACT-018 | 8 | Create pre-demo checklist (30 min prep max) | Scrum Master | M | 2026-06-27 | Not Started |  | Process
ACT-019 | 9 | Create SMART sprint goal template | Scrum Master | H | 2026-07-04 | Not Started |  | Process
ACT-020 | 10 | Create onboarding wiki for new engineers | HR + Tech Lead | H | 2026-07-25 | Not Started |  | People

## Trend Analysis
SPRINT HEALTH TRENDS – [Your Company]
Sprint | Team Mood (1-5) | Goal Achievement % | Actions Completed % | Blockers Count | Velocity (Points) | Notes
1 | 4 | 75 | 67 | 3 | 38 | Good start
2 | 3 | 70 | 80 | 5 | 35 | Testing bottleneck
3 | 4 | 80 | 75 | 2 | 40 | Improving
4 | 3 | 65 | 50 | 6 | 36 | Dependencies issue
5 | 4 | 90 | 88 | 1 | 42 | Tech debt cleared
6 | 4 | 85 | 60 | 2 | 44 | Docs issue emerging
7 | 4 | 88 | 70 | 2 | 45 | Comms improving
8 | 5 | 95 | 75 | 1 | 46 | Best sprint yet
9 | 5 | 100 | 83 | 0 | 48 | Consistent excellence
10 | 5 | 100 | 90 | 0 | 49 | All goals met

## Templates
RETROSPECTIVE TEMPLATES – [Your Company]
TEMPLATE 1: 4L RETROSPECTIVE
LIKED | LEARNED |  | LACKED | LONGED FOR
What did you enjoy? | What did you enjoy? |  | What did you enjoy? | What did you enjoy?
TEMPLATE 2: START / STOP / CONTINUE
START |  | STOP |  | CONTINUE
Actions or practices to begin |  | Actions or practices to begin |  | Actions or practices to begin
TEMPLATE 3: MAD / SAD / GLAD
MAD |  | SAD |  | GLAD
Things frustrating/upsetting the team |  | Things frustrating/upsetting the team |  | Things frustrating/upsetting the team