## Dashboard
[Your Company] — Sprint Velocity Tracker
Team: ___________________ Project: ___________________ Updated: =TODAY()
SPRINT DATA — Enter story points committed and completed for each sprint
Sprint | Sprint Name | Start Date | End Date | Goal | Committed | Completed | Goal Met? | Velocity | Avg (Roll 3) | % Complete | Status | Notes
1 | Sprint 1 | 2026-01-05 | 2026-01-16 | Launch user login module | 42 | 38 | Yes
2 | Sprint 2 | 2026-01-19 | 2026-01-30 | Complete onboarding flow | 45 | 45 | Yes
3 | Sprint 3 | 2026-02-02 | 2026-02-13 | Payment integration v1 | 50 | 40 | No
4 | Sprint 4 | 2026-02-16 | 2026-02-27 | Payment integration v2 | 44 | 44 | Yes
5 | Sprint 5 | 2026-03-02 | 2026-03-13 | Dashboard & reporting | 48 | 46 | Yes
6 | Sprint 6 | 2026-03-16 | 2026-03-27 | Admin panel core | 42 | 42 | Yes
7 | Sprint 7 | 2026-03-30 | 2026-04-10 | Notifications system | 46 | 38 | No
8 | Sprint 8 | 2026-04-13 | 2026-04-24 | API integrations | 50 | 50 | Yes
9 | Sprint 9 | 2026-04-27 | 2026-05-08 | Performance optimisation | 44 | 44 | Yes
10 | Sprint 10 | 2026-05-11 | 2026-05-22 | Mobile responsive design | 48 | 45 | Yes
11 | Sprint 11 | 2026-05-25 | 2026-06-05 | Security hardening | 42 | 42 | Yes
12 | Sprint 12 | 2026-06-08 | 2026-06-19 | Final QA & release prep | 46 | 44 | Yes
TOTALS / AVERAGES
VELOCITY STATISTICS & FORECASTING
Metric | Value | Formula Used | Interpretation
Minimum Velocity (Vmin) |  |  | Conservative forecast — use for pessimistic sprint planning
Maximum Velocity (Vmax) |  |  | Optimistic upper bound — rarely achieved consistently
Average Velocity (Vavg) |  |  | Use as baseline for sprint planning commitments
Velocity Std Deviation |  |  | Smaller = more predictable team; larger = unstable delivery
Sprint Goal Hit Rate |  | COUNTIF(Yes)/total | Target > 80%. Below 60% = planning or execution issue
Total Story Points Done |  | SUM(completed) | Total value delivered across all sprints
Forecast: Sprints to deliver 100 pts |  | 100 / Vavg | Use for release planning — apply Vmin for conservative estimate
Forecast: Sprints to deliver 200 pts |  | 200 / Vavg | Multiply by sprint length for calendar estimate
Forecast: Sprints to deliver 300 pts |  | 300 / Vavg | Combine with team capacity calendar for accuracy
SPRINT CAPACITY PLANNING
Team Member | Role | Availability % | Sprint Days | Capacity Factor | Points Capacity | Notes
Alice Johnson | Developer | 100% | 10 | 70%
Bob Smith | Developer | 100% | 10 | 70%
Carol White | Developer | 80% | 8 | 70% |  | 20% on support rota
David Lee | Developer | 100% | 10 | 70%
Emma Brown | QA Engineer | 100% | 10 | 60%
Frank Chen | Scrum Master | 50% | 5 | 50% |  | 50% other team
TOTAL TEAM CAPACITY (HOURS)

## Velocity Chart
Sprint Velocity Trend Analysis — [Your Company]
Sprint | Committed | Completed | Rolling Avg (3) | Target (Vavg)
Sprint 1 | 42 | 38 | 38 | 43
Sprint 2 | 45 | 45 | 41.5 | 43
Sprint 3 | 50 | 40 | 41 | 43
Sprint 4 | 44 | 44 | 43 | 43
Sprint 5 | 48 | 46 | 43.3 | 43
Sprint 6 | 42 | 42 | 44 | 43
Sprint 7 | 46 | 38 | 42 | 43
Sprint 8 | 50 | 50 | 43.3 | 43
Sprint 9 | 44 | 44 | 44 | 43
Sprint 10 | 48 | 45 | 46.3 | 43
Sprint 11 | 42 | 42 | 43.7 | 43
Sprint 12 | 46 | 44 | 43.7 | 43

## Instructions
HOW TO USE — Sprint Velocity Tracker
SETUP
Team Name | Edit cell B2 on the Dashboard tab to enter your team name
Sprint Count | The tracker is pre-configured for 12 sprints. Add rows to extend.
DATA ENTRY — Dashboard Tab
Sprint Name | Enter a descriptive name for each sprint (e.g. 'Sprint 1 — Login Module')
Start / End Dates | Enter the sprint start and end dates in YYYY-MM-DD format
Sprint Goal | Briefly describe the Sprint Goal (what the team committed to achieve)
Committed | Enter the total story points the team committed at Sprint Planning
Completed | Enter the actual story points completed by Sprint end (met Definition of Done)
Goal Met? | Enter 'Yes' or 'No' — was the Sprint Goal achieved?
Notes | Any context: team absences, scope changes, incidents, new joiners
AUTO-CALCULATED FIELDS
Velocity | Automatically equals story points completed
Rolling Avg (3) | Average velocity over the last 3 sprints — more stable than single-sprint velocity
% Complete | Completed / Committed — shows how accurate sprint planning was
Status | ✓ On Track if Goal Met = Yes, ⚠ Missed if No
VELOCITY STATISTICS
Vmin | Minimum velocity — use for conservative release forecasting
Vavg | Average velocity — use as the default for sprint planning
Vmax | Maximum velocity — use for optimistic upper bound only
Std Deviation | Smaller is better — indicates predictable, stable team output
Sprint Goal Hit Rate | Target > 80%. If below 60%, review planning and execution quality.
CAPACITY PLANNING
Availability % | 100% = full sprint, 80% = 20% on other duties
Sprint Days | Number of working days the person works in the sprint
Capacity Factor | Accounts for meetings, non-dev work. Developer: 0.7, QA: 0.6, SM: 0.5
Points Capacity | Days × Availability × Factor × 8hrs — estimates effective working hours
BEST PRACTICES
Update frequency | Update completed points and goal status within 24hrs of sprint end
Velocity trend | Look for improving or declining trend — investigate anomalies
Planning | Use Vavg for the sprint commitment; never plan to Vmax
Team changes | If team size changes, note it — velocity will shift. Recalibrate after 2–3 sprints.