## Stakeholder Register
STAKEHOLDER REGISTER – [YOUR COMPANY]
Project: Digital Transformation Programme ¦ PM: [Your Name] ¦ Last Updated: 2026-03-30
ID | Name | Role / Organisation | Interest | Influence | Type | Comms Freq | Channel | Key Concerns | Engagement Strategy | Current Level | Notes
STK-001 | James Worthington | Executive Sponsor / CEO | H | H | Internal | Monthly | Face-to-face | Budget, ROI, delivery timelines | Manage Closely — weekly executive updates, key decisions | Engaged | Critical sponsor
STK-002 | [Your Name] | Project Manager | H | H | Internal | Daily | Slack/Teams | All project aspects | Manage Closely — project lead | Highly Engaged
STK-003 | Ahmed Al-Rashid | Product Owner / Tech Lead | H | H | Internal | Daily | Standup/Jira | User stories, backlog, architecture | Manage Closely — co-creation and daily collaboration | Highly Engaged | Key decision maker
STK-004 | Sarah Mitchell | IT Infrastructure Manager | M | H | Internal | Weekly | Email/Teams | Security, compliance, infrastructure | Keep Satisfied — weekly technical briefings | Engaged
STK-005 | Finance Director | Finance Lead | L | H | Internal | Monthly | Email/Report | Budget, spend forecasting, ROI | Keep Satisfied — monthly financial dashboard | Passive | Influencer on budget
STK-006 | Operations Team (15 users) | End Users — Operations | H | L | Internal | Bi-weekly | Demo/Training | Ease of use, workflow disruption | Keep Informed — user testing sessions and demos | Engaged | Primary end users
STK-007 | Sales Team (8 users) | End Users — Sales | H | L | Internal | Bi-weekly | Demo/Slack | CRM integration, pipeline impact | Keep Informed — demos and workshops | Partially Engaged
STK-008 | Legal & Compliance Officer | Legal / Compliance | M | H | Internal | Monthly | Email | GDPR, data handling, regulatory risk | Keep Satisfied — compliance reviews | Engaged | Critical for legal sign-off
STK-009 | CloudTech Solutions | Vendor / AWS Partner | M | M | External Vendor | Weekly | Email/Teams | Contract, delivery SLAs | Manage Vendor — weekly vendor calls | Engaged | Strategic partner
STK-010 | HR Director | Human Resources | M | M | Internal | Monthly | Email | Staff impact, change management | Keep Informed — HR briefings | Passive
STK-011 | Marketing Lead | Marketing | L | L | Internal | Quarterly | Email | Brand alignment, customer comms | Monitor — quarterly newsletter updates | Passive
STK-012 | Al Futtaim Group | Enterprise Client | H | M | External Client | Bi-weekly | Call/Demo | Solution quality, delivery pace | Keep Informed — progress demos and updates | Engaged | Key reference client
STK-013 | UAE Regulatory Body | Government Regulator | L | H | Regulator | Quarterly | Formal Report | Data residency, compliance | Keep Satisfied — formal quarterly reporting | Passive | Must not ignore
STK-014 | Senior Developer Lead | Engineering Team | H | M | Internal | Daily | Slack/Standup | Technical decisions, architecture | Keep Informed — technical design reviews | Highly Engaged
STK-015 | QA Lead | Quality Assurance | H | M | Internal | Daily | Jira/Slack | Test coverage, quality standards | Keep Informed — testing strategy sessions | Highly Engaged

## Power-Interest Grid
POWER-INTEREST GRID – [YOUR COMPANY]
| LOW INTEREST | HIGH INTEREST
HIGH POWER | KEEP SATISFIED | MANAGE CLOSELY
| STK-005 — Finance Director | STK-001 — James Worthington (Executive Sponsor)
| STK-008 — Legal & Compliance | STK-002 — [Your Name] (PM)
| STK-013 — UAE Regulatory Body | STK-003 — Ahmed Al-Rashid (PO/Tech Lead)
STK-004 — IT Infrastructure Mgr
LOW POWER | MONITOR | KEEP INFORMED
| STK-010 — HR Director | STK-006 — Operations Team (End Users)
| STK-011 — Marketing Lead | STK-007 — Sales Team (End Users)
STK-012 — Al Futtaim Group (Client)
STK-014 — Senior Developer Lead
STK-015 — QA Lead

## Communication Plan
STAKEHOLDER COMMUNICATION PLAN – [YOUR COMPANY]
Define how and when to communicate with each stakeholder
Stakeholder | Type | Frequency | Format | Owner | Purpose | Key Messages | Next Due
James Worthington | Executive Sponsor | Monthly | Executive Summary | [Your Name] | Strategic decisions and budget sign-off | Project health, financials, risks, decisions needed | 2026-04-30
Ahmed Al-Rashid | Product Owner | Daily | Standup + Jira | PM/Scrum Master | Backlog alignment and delivery priorities | Sprint progress, blockers, priority changes | Daily
Sarah Mitchell | IT Infrastructure | Weekly | Teams Call | DevOps Lead | Technical alignment and infrastructure readiness | Infrastructure status, security review updates | 2026-04-04
Finance Director | Finance | Monthly | Financial Report | PM + Finance | Budget tracking and forecast review | Spend vs budget, forecast to complete, risks | End of month
Legal & Compliance | Compliance | Monthly | Email + Meeting | PM + Legal | Compliance review and risk management | GDPR status, data handling approach, open issues | 2026-04-15
Operations Team | End Users | Bi-weekly | Demo + Workshop | Product Owner | User feedback and adoption readiness | Feature updates, training plans, feedback collection | 2026-04-10
Sales Team | End Users | Bi-weekly | Demo | Product Owner | CRM integration updates and user readiness | Feature walkthroughs, Q&A, go-live preparation | 2026-04-17
CloudTech (Vendor) | Vendor | Weekly | Teams Call | DevOps Lead | Technical delivery and SLA management | Deployment status, issues, upcoming changes | Weekly
HR Director | HR | Monthly | Email + Brief | PM | Change management and team wellbeing | Staff impact summary, training needs, timeline | 2026-04-30
Al Futtaim Group | Enterprise Client | Bi-weekly | Demo Call | PM + Account Mgr | Client confidence and feature validation | Delivery progress, demo, upcoming milestones | 2026-04-10
UAE Regulatory Body | Regulator | Quarterly | Formal Report | Legal Lead | Regulatory compliance reporting | Compliance status, data residency, certifications | 2026-06-30
Senior Dev Lead | Engineering | Daily | Standup + PR Review | Tech Lead | Technical decisions and code quality | Architecture decisions, code review, tech debt | Daily
QA Lead | Quality Assurance | Daily | Standup + Jira | Scrum Master | Test coverage and quality gate status | Test execution, defects, UAT readiness | Daily
Marketing Lead | Marketing | Quarterly | Email | PM | Brand and external comms alignment | Go-live date, customer impact, press approach | 2026-06-30
IT Infrastructure Mgr | IT | Weekly | Email | DevOps Lead | Infrastructure provisioning and security | Environment status, security findings, SLA | Weekly